## How to use
Requirements traceability matrix (RTM): how to use
What it is for
A table that links each requirement to the design document that meets it, the check that verifies it and the record that proves it. Equipment suppliers use it after award when a contract asks them to show every requirement was met, and to find what a change affects.
Steps
Step 1 | Fix the baseline: the purchase order, the specification and datasheet revisions, and the agreed deviation list. Put them in the header block.
Step 2 | Give every requirement its own row and a unique ID that never changes. Split clauses that hold more than one requirement.
Step 3 | Where an agreed deviation or concession changes a requirement, note it in the Agreed deviation column, so you verify what was agreed, not the original wording.
Step 4 | For each row, name the design document that meets it and the verification method: test, inspection, analysis, demonstration or review.
Step 5 | Link each row to where the check is planned, usually an inspection and test plan (ITP) step or a test procedure.
Step 6 | When the check is done, add the record number in Evidence and set the status. Failed rows turn red and Concession rows amber.
Step 7 | When a specification or drawing changes, filter the Source document or Design reference column to find every row it affects.
Step 8 | Before handover, filter Status for anything that is not Verified or Concession. Every such row needs an action or an agreed deviation.
Verification methods
Test | Measure the item under set conditions, such as a pressure or leak test.
Inspection | Look at or measure the item or its records, such as a dimensional check or certificate review.
Analysis | Show by calculation or model, such as a wall-thickness or torque calculation.
Demonstration | Operate the item and show it works, without detailed measurement.
Review | Check a document against the requirement, such as a drawing or procedure approval.
Columns
Req ID | A unique ID that never changes, even if the clause is renumbered.
Source document | The document the requirement comes from, with revision.
Clause | Clause, datasheet line or PO item.
Requirement | The requirement in the source's words, or a short faithful summary for long clauses.
Type | Mandatory (shall), Advisory (should) or Information (drop-down).
Agreed deviation | The agreed deviation or concession that changes this requirement, if any.
Design reference | The drawing, datasheet, calculation or procedure that meets the requirement.
Verification method | Test, Inspection, Analysis, Demonstration or Review (drop-down).
Verification reference | Where the check is planned: ITP step, test procedure or review step.
Evidence (record) | The record that proves it: report, certificate or returned document, with number.
Status | Open, Planned, In progress, Verified, Failed or Concession (drop-down). Failed rows turn red; Concession rows amber.
Owner | Who closes the row.
Remarks | Anything a reviewer needs, such as a linked change or open NCR.
Before you use it
The working sheet is blank. The example sheet shows filled-in rows for an invented valve order (PO-EX-3105, specification PS-VAL-001). Delete the example sheet before you send the file.
Every example value is invented: the project, customer, purchase order and every document, transmittal and report number do not exist. Standards are named but not quoted.
If the customer supplies its own register or matrix format, copy your rows into that format rather than sending a second table.
Drop-down lists accept only the listed values. To add a value, edit the list under Data, then Data validation.
Guide and latest version: https://odysseygpt.ai/resources/templates/requirements-traceability-matrix-template
Free template from OdysseyGPT (https://odysseygpt.ai/resources/templates/requirements-traceability-matrix-template). CC BY 4.0: use and adapt it, including in paid bids, and keep this attribution.

## RTM
Requirements traceability matrix (RTM)
Free template from OdysseyGPT (https://odysseygpt.ai/resources/templates/requirements-traceability-matrix-template). CC BY 4.0: use and adapt it, including in paid bids, and keep this attribution.
Project | [5 empty] | Customer
Purchase order | [5 empty] | Baseline documents
Equipment / package | [5 empty] | RTM no.
Revision | [5 empty] | Date
Prepared by | [5 empty] | Checked by
Req ID | Source document | Clause | Requirement | Type | Agreed deviation | Design reference | Verification method | Verification reference | Evidence (record) | Status | Owner | Remarks

## Example (PO-EX-3105)
Requirements traceability matrix (RTM): example
EXAMPLE ONLY. Every value on this sheet is invented: specification PS-VAL-001 and every document, certificate and report number do not exist. Standards are named but not quoted; check against your licensed copies.
Project |  | Example Gas Compression Station, Phase 2 (fictional) |  |  |  | Customer |  | Example EPC Contractor Ltd (fictional)
Purchase order |  | PO-EX-3105 (fictional) |  |  |  | Baseline documents |  | PS-VAL-001 Rev 2; MR-VAL-001 Rev 1; agreed deviation list TDL-EX-2291 Rev B
Equipment / package |  | Trunnion-mounted ball valves, 6 in, ASME Class 600 |  |  |  | RTM no. |  | RTM-EX-3105
Revision |  | B |  |  |  | Date |  | 2026-12-04
Prepared by |  | Project engineer |  |  |  | Checked by |  | Quality engineer
Req ID | Source document | Clause | Requirement | Type | Agreed deviation | Design reference | Verification method | Verification reference | Evidence (record) | Status | Owner | Remarks
R-001 | PS-VAL-001 Rev 2 | 3.1 | Valves shall be designed, manufactured and tested to API 6D. | Mandatory (shall) |  | GA-BV-0600 Rev B; DS-BV-0600 Rev B | Review | ITP-BV-01 step 1 (design review) | GA-BV-0600 Rev B returned code 1 | Verified | Design engineer
R-002 | PS-VAL-001 Rev 2 | 3.4 | The design minimum temperature shall be −46 °C. | Mandatory (shall) | EX-01 (clarified) | DS-BV-0600 Rev B line 9 | Review | ITP-BV-01 step 1 | TQ-EX-007 answer: −46 °C governs | Verified | Proposal engineer
R-003 | PS-VAL-001 Rev 2 | 4.2 | Body and closures shall be forged ASTM A350 LF2 Class 1. | Mandatory (shall) |  | BOM-BV-0600 Rev A items 1–3 | Inspection | ITP-BV-01 step 3 (material certificate review) | MTR set MTR-BV-SET, heats H-1001 to H-1004 | In progress | Quality engineer | Two of four heats received.
R-004 | PS-VAL-001 Rev 2 | 4.5 | Seat inserts shall be PEEK. | Mandatory (shall) | EX-03 (accepted: RPTFE) | DS-BV-0600 Rev B line 18 | Inspection | ITP-BV-01 step 5 (assembly check) |  | Concession | Quality engineer | Verify RPTFE per accepted deviation, not PEEK.
R-005 | PS-VAL-001 Rev 2 | 7.2 | Pressure-containing parts shall have EN 10204 type 3.2 certificates. | Mandatory (shall) |  | QP-01 Rev C | Inspection | ITP-BV-01 step 3 |  | Planned | Quality engineer | Third-party inspector booked for 3.2 witness.
R-006 | PS-VAL-001 Rev 2 | 9.4 | Valves shall be pressure tested (shell and seat). | Mandatory (shall) | EX-08 (accepted: API 6D tests) | TP-BV-02 Rev A | Test | ITP-BV-01 step 8 (witness point) |  | Planned | Test engineer | Test procedure still to be approved.
R-007 | PS-VAL-001 Rev 2 | 10.2 | Gear operators shall be sized for 1.5 times maximum breakaway torque. | Mandatory (shall) |  | Torque calculation TQ-BV-06 Rev B | Analysis | ITP-BV-01 step 2 | TQ-BV-06 Rev B returned code 3 | Failed | Design engineer | Calculation used 1.3; resubmit at 1.5.
R-008 | MR-VAL-001 Rev 1 | 7.1 | Vendor documents shall be submitted as listed in the VDRL. | Mandatory (shall) |  | Vendor document register VDR-EX-3105 | Review | Monthly register review | VDR-EX-3105 Rev C | In progress | Document controller