## How to use
Vendor document register: how to use
What it is for
The register a supplier keeps after award to track every document the purchase order's vendor data requirements list (VDRL) asks for: due date, current revision, transmittal, the customer's review code and the next action. It also maps each final document to its section of the manufacturing record book (MRB).
Steps
Step 1 | Fill in the header block: project, customer, purchase order, the VDRL and its revision, and who keeps the register.
Step 2 | Add one row for every line on the customer's vendor data requirements list (VDRL), plus any document the purchase order or specification asks for that the VDRL misses.
Step 3 | Copy each VDRL code and timing rule, then work out the due date for this order from the PO date and the schedule.
Step 4 | Give each document your number and, if the project uses its own numbering, the customer's number.
Step 5 | Each time you send a revision, update Current rev, Date issued and Transmittal no. When the customer returns it, record the date and review code.
Step 6 | Set the status from the drop-down and write the next action and owner. Rows past their due date that are not Accepted or Closed turn red; rows returned for resubmission turn amber.
Step 7 | Fill in the Data book section for each final document, so the manufacturing record book (MRB) index is built as the order runs, not at the end.
Step 8 | Issue the register to the customer at the agreed interval, with a new revision letter each time.
Review codes (common meanings; use the project's own legend)
1: Accepted | Accepted as issued. Work may go ahead. Keep the returned copy with its stamp.
2: Accepted with comments | Work may usually go ahead, but you must update the document for the comments and resubmit. Check the project legend.
3: Rejected and resubmit | Not accepted. Do not rely on it. Revise and resubmit, answering every comment.
4: Information only | Received for the buyer's records. No formal approval follows.
None yet | Issued and waiting for the buyer's return.
Columns
Item | Running number.
VDRL code | The line or code on the customer's vendor data requirements list (VDRL) that asks for the document.
Document title | Title as the customer will see it. Match the VDRL wording where you can.
Vendor doc no. | Your own document number.
Customer doc no. | The project number the customer assigned, if the project uses its own numbering.
Purpose | For approval, For review, For information or Final (data book) (drop-down).
Due (rule) | The VDRL timing rule, such as "4 weeks after PO" or "before FAT".
Due date | The date that rule gives for this order (YYYY-MM-DD).
Current rev | The latest revision you issued.
Date issued | Date the current revision was sent.
Transmittal no. | The transmittal that sent the current revision.
Date returned | Date the customer returned the current revision.
Review code | The code the customer gave. The drop-down uses common meanings; replace it with the project's own legend.
Status | Not started, In preparation, Issued, Returned: resubmit, Accepted or Closed (drop-down). Rows past due and not Accepted or Closed turn red.
Next action | The next step, and who is waiting on whom.
Owner | Who owns the next action.
Data book section | Where the final version goes in the manufacturing record book (MRB), if it goes in at all.
Remarks | Anything else, such as a sub-supplier the document depends on.
Before you use it
The working sheet is blank. The example sheet shows filled-in rows for an invented valve order (PO-EX-3105, specification PS-VAL-001). Delete the example sheet before you send the file.
Every example value is invented: the project, customer, purchase order and every document, transmittal and report number do not exist. Standards are named but not quoted.
If the customer supplies its own register or matrix format, copy your rows into that format rather than sending a second table.
Drop-down lists accept only the listed values. To add a value, edit the list under Data, then Data validation.
Guide and latest version: https://odysseygpt.ai/resources/templates/vendor-document-register-template
Free template from OdysseyGPT (https://odysseygpt.ai/resources/templates/vendor-document-register-template). CC BY 4.0: use and adapt it, including in paid bids, and keep this attribution.

## Register
Vendor document register
Free template from OdysseyGPT (https://odysseygpt.ai/resources/templates/vendor-document-register-template). CC BY 4.0: use and adapt it, including in paid bids, and keep this attribution.
Project | [5 empty] | Customer
Purchase order | [5 empty] | Material requisition / VDRL
Equipment / package | [5 empty] | Register no.
Revision | [5 empty] | Date
Prepared by | [5 empty] | Checked by
Item | VDRL code | Document title | Vendor doc no. | Customer doc no. | Purpose | Due (rule) | Due date | Current rev | Date issued | Transmittal no. | Date returned | Review code | Status | Next action | Owner | Data book section | Remarks

## Example (PO-EX-3105)
Vendor document register: example
EXAMPLE ONLY. Every value on this sheet is invented: specification PS-VAL-001 and every document, certificate and report number do not exist. Standards are named but not quoted; check against your licensed copies.
Project |  | Example Gas Compression Station, Phase 2 (fictional) |  |  |  | Customer |  | Example EPC Contractor Ltd (fictional)
Purchase order |  | PO-EX-3105 (fictional) |  |  |  | Material requisition / VDRL |  | MR-VAL-001 Rev 1 / VDRL-VAL-001 Rev 1
Equipment / package |  | Trunnion-mounted ball valves, 6 in, ASME Class 600 |  |  |  | Register no. |  | VDR-EX-3105
Revision |  | C |  |  |  | Date |  | 2026-12-04
Prepared by |  | Document controller |  |  |  | Checked by |  | Project manager
Item | VDRL code | Document title | Vendor doc no. | Customer doc no. | Purpose | Due (rule) | Due date | Current rev | Date issued | Transmittal no. | Date returned | Review code | Status | Next action | Owner | Data book section | Remarks
1 | A01 | General arrangement drawing | GA-BV-0600 | EX-3105-V-GA-001 | For approval | 4 weeks after PO | 2026-11-12 | B | 2026-11-26 | TR-EX-3105-004 | 2026-12-02 | 1: Accepted | Accepted | None. Rev B accepted. | Design engineer | 2.1 | Rev A returned code 2 on 2026-11-19.
2 | A02 | Valve datasheets (as offered) | DS-BV-0600 | EX-3105-V-DS-001 | For approval | 4 weeks after PO | 2026-11-12 | A | 2026-11-10 | TR-EX-3105-002 | 2026-11-24 | 2: Accepted with comments | Returned: resubmit | Add seat material per agreed deviation EX-03; issue Rev B. | Proposal engineer | 2.2
3 | B01 | Inspection and test plan (ITP) | ITP-BV-01 | EX-3105-V-ITP-001 | For approval | Before manufacture | 2026-11-20 | A | 2026-11-18 | TR-EX-3105-003 |  | None yet | Issued | Chase return; manufacture waits on approval. | Quality engineer | 1.3 | Hold point: manufacture not released until approved.
4 | B02 | Hydrostatic and seat test procedure | TP-BV-02 | EX-3105-V-PRO-002 | For approval | 6 weeks before FAT | 2026-12-01 |  |  |  |  | None yet | In preparation | Finish draft; internal check. | Test engineer | 5.1 | Past due.
5 | B05 | Painting procedure | PP-BV-01 | EX-3105-V-PRO-005 | For review | Before painting | 2027-01-15 |  |  |  |  | None yet | Not started | Request coating supplier data sheet. | Quality engineer | 6.1 | Depends on coating supplier.
6 | C01 | Material certificates, pressure parts (EN 10204 3.1) | MTR-BV-SET | EX-3105-V-CER-001 | Final (data book) | With data book | 2027-03-01 |  |  |  |  | None yet | In preparation | Collect certificates as material arrives; check against PO. | Quality engineer | 3.1 | Certificate type per agreed deviation EX-06.
7 | D01 | Installation, operation and maintenance manual | IOM-BV-0600 | EX-3105-V-MAN-001 | For review | 4 weeks before shipment | 2027-02-01 |  |  |  |  | None yet | Not started | Start from standard manual; add project tags. | Design engineer | 8.1
8 | E01 | Final manufacturing record book (MRB) | MRB-EX-3105 | EX-3105-V-MRB-001 | Final (data book) | 4 weeks after shipment | 2027-04-12 |  |  |  |  | None yet | Not started | Ask customer for the MRB index now. | Document controller |  | Payment milestone tied to acceptance (see PO).